## Slide 1
Project SABR
This Week · Aug 6, 2026
8/6 Update
Beta: Sep 30, 2026 · 55 days remaining
HIGHLIGHTS:
MVPD: Mobile now has a working build with DRM and picture-in-picture confirmed on-device. MVPD provider login ("sign in with your TV provider") is currently the only way into the app, since it's required before any video will play.
VOD: The replay processing pipeline is now running against real production matches and data, with output already viewable in the dev environment. The team is coordinating with Amagi on getting replays flowing to Roku as well.
STATUS UPDATE:
ROKU INTEGRATION: Resolved a metadata conflict between Premium Subscriptions and Roku by removing the conflicting sports event feed from OTT, simplifying the implementation path. Amagi's monitoring UI for match visibility is on track for mid-August delivery, giving Roku read-only access to what's live without Tennis Channel maintaining manual availability sheets by hand. Linear stream reconnection is complete, and ad testing is underway pending final connection confirmation.
FRONTEND UX AND DESIGN: Engineering delivered prototypes for the tournaments and live pages this week. With Claude helping engineers move quickly and ship continuously, the team is starting twice-weekly design jam sessions (Tuesdays and Thursdays, first one August 6) so engineers, design, and stakeholders can review in-flight work and align on priorities in step with that pace.
MERCHANDISING AND CAROUSELS: Landed on "show more" link behavior across platforms: on by default, off entirely, or a custom label and destination. Default item limit is twenty, with each device able to override based on its own performance needs. Still to be settled: placing the show-more link as a full tile at the end of the carousel, treated as a near-term priority for TV apps since the team believes it would meaningfully improve discovery over today's plain title-link approach.
BACKEND AND PLAYBACK: DRM playback and picture-in-picture are confirmed working on real mobile devices after Akash, Alex, and Aaron patched an iOS certificate issue; a working build with MVPD login goes out once final testing wraps. The team is standing up a CI pipeline for iOS and Android so builds reach staging and TestFlight several times a week instead of ad hoc, speeding up feedback. Yisake finished decoupling the profile screen from the main menu and is now building email-change functionality, with the backend piece already in place. Erik's team spent the week on the tournaments and live pages, with follow-up design conversations already scheduled.
AMAGI INTEGRATION: Amagi proposed a significant upgrade to DVR and VOD: instead of one shared stream manually reset between matches, each match gets its own dedicated address that automatically switches from live to replay at match end, with a buffer window so mid-match viewers aren't cut off. The team raised good questions on URL predictability, security tokens, and edge cases like joining late; Amagi is drafting a written proposal this week with a working demo targeted for mid-August. Brian Hoskins delivered the data matrix Amagi needs for ad targeting, so both teams can move quickly on ad requirements. The Tennis Channel-specific EPG is being built out, and Roku flagged a certification requirement for scrub-bar thumbnail previews that Dave and Swamy are syncing on this week.
CONTENT AND METADATA: SportRadar login/consent tracking is moving to a new test environment, so existing test accounts won't carry over and will need to be recreated. The team is still tracking down where SportRadar stores users' favorited players so that data can migrate cleanly. Replay processing is active on real matches, with WSC-sourced replays already running through the pipeline and visible in dev. Rain-delay trimming and ad-supported VOD strategy remain future conversations, pending a broader ad-fill discussion.
KEY DECISIONS:
1. Beta target confirmed for September 30, with testing running through roughly December.
2. Tennis Channel O&Os remain on Cleeng for payment/subscription at MVP; a post-launch review will separately evaluate a Recurly transition (full project, roughly one quarter).
3. Out-of-scope features will enter a formal backlog and roadmap prioritization process rather than being added ad hoc.
4. Device feature parity will be secondary; web and mobile go live first, with living-room platforms catching up after.
5. MultiView designated P1, post-launch.
6. GraceNote will not be used for EPG management; the team will use Amagi's platform capabilities instead.
7. Bitmovin will be the primary launch analytics/observability platform for streaming performance.
8. Coupon/offer configuration stays in Cleeng as-is; promotions use a manual price override on the plan page rather than new tooling before launch.
9. Tennis Channel keeps its existing token/URL security approach for launch.
Project SABR · Tennis Channel OTT · CONFIDENTIAL
9% Ready

## Slide 2
Project SABR
Critical Gates · Aug 6, 2026
Vendor / Contract
Bitmovin
Contract signed 7/15.
Contracted
Adobe
We are good.
Contracted
Amagi SOW
M15 and Highlights will deliver via Amagi. Back-catalog VOD through Aspera; newer content (S3) handled separately. Amagi generating public key for Roku credential exchange.
Contracted
FOXXUM
Integration ongoing. TV cert submission tied to November 1 deadline. UX change catalog being drafted for Foxxum coordination. Contract signature unconfirmed as of 7/15.
In Progress
Amplitude
Decided, moving forward. Pricing confirmed at roughly half their initial offer (cheaper than what Wealthfront charged for similar volume), setup fee waived, and the team confirmed they want it, including integrating with Foxxum. Ari is proceeding to get the contract signed.
In Progress
SR Data
Bulk VOD ingest of 30,000+ assets planned. Manual media ingest workflow for content team (non-bulk uploads). VOD replace/hide workaround in place as interim solution.
In Progress
Shared Infrastructure & Dev Tooling
Monitoring & Error Tracking
Google Analytics data is unreliable, so the team is evaluating Amplitude, Mixpanel, and PostHog as replacements and adding backend safeguards to catch errors automatically.
In Progress
New Mobile App
A new TestFlight build shipped this week, and DRM playback with picture-in-picture is now confirmed working on a real device after an iOS certificate fix.
In Progress
New Website
Engineers began prototyping the new tournaments and live pages, and the team kicked off twice-weekly design jam sessions to keep design and engineering aligned.
In Progress
Hosting
No new update this week.
Contracted
Analytics Data Warehouse
No new update this week.
In Progress
Partner / Platform Integrations
MVPD
MVPD (TV-provider) login is now the only way into the mobile app, with a login fix still being finalized for Android.
Complete
DRM
The iOS certificate issue is fixed, and DRM playback with picture-in-picture is confirmed working on a real device.
In Progress
FOXXUM
Foxxum demoed the new content page and carousel pagination, and is now focused on entitlement checks, with playback migration, geo-blocking, and concurrency limits queued up next.
In Progress
Platform Capabilities
Platform POC
The team is migrating off the limited trial Auth0 account onto a proper dev tenant, and the vendor confirmed the new account request.
Complete
UI/UX
Every carousel will keep a default "show more" link with item limits set per device, and design jam sessions started this week.
In Progress
Video Player
No BitMovin-specific update this week, but DRM playback with picture-in-picture is confirmed working on iOS.
In Progress
Testing
The team is building a CI pipeline to push iOS and Android builds to staging and TestFlight more frequently.
In Progress

## Slide 3
Project SABR
CPR · Aug 6, 2026
3 Done
29 In Progress
3 Not Started
0 Blocked
Sep 30, 2026 · Beta
Project SABR · Tennis Channel OTT · CONFIDENTIAL
Beta: Sep 30, 2026 · 55 days remaining
9% Ready
Platforms
6 / 7 In Progress
TC.com
In Progress
iOS
In Progress
Android
In Progress
Roku
In Progress
Fire TV
Not Started
Samsung
In Progress
tvOS
In Progress
Video
Delivery
6 / 6 In Progress
HLS
In Progress
MPEG-DASH
In Progress
FairPlay DRM
In Progress
Widevine DRM
In Progress
VOD Streams
In Progress
Linear
In Progress
Player
5 / 5 In Progress
Web Player
In Progress
iOS Player
In Progress
Android Player
In Progress
HLS/DASH PB
In Progress
Bitmovin QOE
In Progress
Merchandising
6 / 9 In Progress · 2 Done
Metadata
In Progress
Images
In Progress
Carousels
In Progress
Live Events
In Progress
Back Catalog
Not Started
Full Replays
In Progress
M15
Done
Highlights
Done
Linear
In Progress
Onboarding
4 / 6 In Progress · 1 Done
Unentitled
In Progress
Sign-in
In Progress
Subscription
In Progress
MVPD
Done
Cleeng
In Progress
Promos
Not Started
Data
& Analytics
2 / 2 In Progress
NPAW Historical
In Progress
Cleeng Historical
In Progress
Milestones
Requirements
Jun 30, 2026
Complete
Beta
Sep 30, 2026
In Progress
UAT / Testing
Nov 30, 2026
Upcoming
Release
Dec 2026
Upcoming
Status Key
Not Started
Work has not begun
In Progress
Active development underway
Blocked
Blocked by dependency
Done
Complete ✓
At Risk
NS with unmet dependencies

## Slide 4
Project SABR · TC.com
Web Browser · Aug 6, 2026
3 Done
15 In Progress
2 Not Started
0 Blocked
Sep 30, 2026 · Beta
Project SABR · Tennis Channel OTT · CONFIDENTIAL
Beta: Sep 30, 2026 · 55 days remaining
15% Ready
Video
Delivery
3 / 3 In Progress
HLS
In Progress
VOD Streams
In Progress
Linear
In Progress
Player
2 / 2 In Progress
Web Player
In Progress
HLS/DASH PB
In Progress
Merchandising
6 / 9 In Progress · 2 Done
Metadata
In Progress
Images
In Progress
Carousels
In Progress
Live Events
In Progress
Back Catalog
Not Started
Full Replays
In Progress
M15
Done
Highlights
Done
Linear
In Progress
Onboarding
4 / 6 In Progress · 1 Done
Unentitled
In Progress
Sign-in
In Progress
Subscription
In Progress
MVPD
Done
Cleeng
In Progress
Promos
Not Started
Milestones
Requirements
Jun 30, 2026
Complete
Beta
Sep 30, 2026
In Progress
UAT / Testing
Nov 30, 2026
Upcoming
Release
Dec 2026
Upcoming
Status Key
Not Started
In Progress
Blocked
Done

## Slide 5
Project SABR · iOS
iPhone · iPad · Aug 6, 2026
3 Done
16 In Progress
2 Not Started
0 Blocked
Sep 30, 2026 · Beta
Project SABR · Tennis Channel OTT · CONFIDENTIAL
Beta: Sep 30, 2026 · 55 days remaining
14% Ready
Video
Delivery
4 / 4 In Progress
HLS
In Progress
FairPlay DRM
In Progress
VOD Streams
In Progress
Linear
In Progress
Player
2 / 2 In Progress
iOS Player
In Progress
HLS/DASH PB
In Progress
Merchandising
6 / 9 In Progress · 2 Done
Metadata
In Progress
Images
In Progress
Carousels
In Progress
Live Events
In Progress
Back Catalog
Not Started
Full Replays
In Progress
M15
Done
Highlights
Done
Linear
In Progress
Onboarding
4 / 6 In Progress · 1 Done
Unentitled
In Progress
Sign-in
In Progress
Subscription
In Progress
MVPD
Done
Cleeng
In Progress
Promos
Not Started
Milestones
Requirements
Jun 30, 2026
Complete
Beta
Sep 30, 2026
In Progress
UAT / Testing
Nov 30, 2026
Upcoming
Release
Dec 2026
Upcoming
Status Key
Not Started
In Progress
Blocked
Done

## Slide 6
Project SABR · Android
Android Phone · Tablet · Aug 6, 2026
3 Done
17 In Progress
2 Not Started
0 Blocked
Sep 30, 2026 · Beta
Project SABR · Tennis Channel OTT · CONFIDENTIAL
Beta: Sep 30, 2026 · 55 days remaining
14% Ready
Video
Delivery
5 / 5 In Progress
HLS
In Progress
MPEG-DASH
In Progress
Widevine DRM
In Progress
VOD Streams
In Progress
Linear
In Progress
Player
2 / 2 In Progress
Android Player
In Progress
HLS/DASH PB
In Progress
Merchandising
6 / 9 In Progress · 2 Done
Metadata
In Progress
Images
In Progress
Carousels
In Progress
Live Events
In Progress
Back Catalog
Not Started
Full Replays
In Progress
M15
Done
Highlights
Done
Linear
In Progress
Onboarding
4 / 6 In Progress · 1 Done
Unentitled
In Progress
Sign-in
In Progress
Subscription
In Progress
MVPD
Done
Cleeng
In Progress
Promos
Not Started
Milestones
Requirements
Jun 30, 2026
Complete
Beta
Sep 30, 2026
In Progress
UAT / Testing
Nov 30, 2026
Upcoming
Release
Dec 2026
Upcoming
Status Key
Not Started
In Progress
Blocked
Done

## Slide 7
Project SABR · FOXXUM
Roku · Fire TV · Samsung · tvOS · Aug 6, 2026
3 Done
19 In Progress
2 Not Started
0 Blocked
Sep 30, 2026 · Beta
Covers:
Roku
Fire TV
Samsung
tvOS
Project SABR · Tennis Channel OTT · CONFIDENTIAL
Beta: Sep 30, 2026 · 55 days remaining
13% Ready
Video
Delivery
6 / 6 In Progress
HLS
In Progress
MPEG-DASH
In Progress
FairPlay DRM
In Progress
Widevine DRM
In Progress
VOD Streams
In Progress
Linear
In Progress
Player
3 / 3 In Progress
iOS Player
In Progress
Android Player
In Progress
HLS/DASH PB
In Progress
Merchandising
6 / 9 In Progress · 2 Done
Metadata
In Progress
Images
In Progress
Carousels
In Progress
Live Events
In Progress
Back Catalog
Not Started
Full Replays
In Progress
M15
Done
Highlights
Done
Linear
In Progress
Onboarding
4 / 6 In Progress · 1 Done
Unentitled
In Progress
Sign-in
In Progress
Subscription
In Progress
MVPD
Done
Cleeng
In Progress
Promos
Not Started
Milestones
Requirements
Jun 30, 2026
Complete
Beta
Sep 30, 2026
In Progress
UAT / Testing
Nov 30, 2026
Upcoming
Release
Dec 2026
Upcoming
Status Key
Not Started
In Progress
Blocked
Done